## Sheet1
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | PERCENT COMPLETE
Planning and Overview
| Initial research | 2024-08-01 | 2024-08-07 | 0 | 7 | 100%
| Formation of research questions | 2024-08-02 | 2024-08-08 | 1 | 7 | 100%
| Proposal (excl. Lit review) | 2024-08-03 | 2024-08-09 | 2 | 7 | 100%
| Initial literature review | 2024-08-04 | 2024-08-25 | 3 | 22 | 10%
Part 1: Classification with CT
| Noise Simulation with xcist | 2024-08-25 | 2024-08-30 | 24 | 6 | 0%
| Set up method with CT Classification | 2024-08-30 | 2024-09-06 | 29 | 8 | 0%
| Improve Efficiency (using OpenCL or C++) | 2024-09-06 | 2024-09-11 | 36 | 6 | 0%
Part 2: Extensions (Segmentation & Datasets)
| Apply to Segmentation Problem | 2024-09-11 | 2024-09-20 | 41 | 10 | 0%
| Refine Model & Overall Architecture/Design | 2024-09-20 | 2024-09-25 | 50 | 6 | 0%
| Apply to other Datasets | 2024-09-25 | 2024-09-25 | 55 | 1 | 0%
Final Write Up
| Compile Results | 2024-09-25 | 2024-09-30 | 55 | 6 | 0%
| Compare results to original research question | 2024-09-25 | 2024-09-30 | 55 | 6 | 0%
| Body of report write up | 2024-09-30 | 2024-10-04 | 60 | 5 | 0%
| Editing and corrections | 2024-10-04 | 2024-10-15 | 64 | 12 | 0%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1